## V1
Project Development and Completion Tracker
Porject ID: Version 1.2 (Flutter)
Project Start Date: 15-03-2021 Project End Date:
Porject Descreption:
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members | Suhanee Hingorani | Team Lead | Project Development Student Team Memebers | Suhanee Hingorani |  | Team Leads | Project Domain Expert Team Members (Geolife)
| Vilakshan | Team Member |  | Suhanee Hingorani | Vilakshan | Frond End
Team Lead
Front/Back End
Back End
Front End
Epic: | As a farmer, I should know fertilizer requirement for my crop in my region to fulfill N,P,K. (Nitrogen, Phosphorus, Potassium)
Story 1: | As a farmer, I should know N,P,K contribution from soil of my farm.
Story 2: | As a farmer, I should know N,P,K requirement of crop for mentioned production.
Story 3: | As a farmer, need reccomendation of fertilizer to fulfil N,P,K requiremnt of my crop.
Task1: | Design farmer registration layout with database configuration.
Task2: | Design login page layout.
Task3: | Design region selection layout on google map with database mapping to retrieve N,P,K value as per predefined region.
Task4: | Design Crop selection layout which mapps with database having crop data and provide selction of crop efficacy to acheive.
Task5: | Design layout to calculate N,P,K requirement for the crop to acheive effiicacy selected in Task4.
Task6: | Design layout to reccomond fertilizer from database which fulfils N,P,K requirement caluclated in Task5.
Acceptance Criteria:
1 | Registration layout is following all registration inputs with validations for suitable and correct data.
2 | login layout suports gmail/ contact number/ Aadhar number (future scope) credetials with input validations.
3 | Region selection can be easilty done by entering pincode or google map location and shows approximate N, P, K values of that region.
4 | Crop selection layout with reach UX design provide list of crop appropriate for region and season (calendar month) along with efficacy selection slider.
5 | Fertilizer recommendation layout shows approximate N,P,K requirement for the crop and required amount of fertilizert to fulfil requirement calculated.
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 0 | Design farmer registration layout with database configuration. | Layout Design | Complete | Anjali, Shruti | 2022-02-03 | 2022-02-12 | 2022-02-04 |  | 100% | Not Started | Medium
|  | Database configuration | Complete | Anjali, Shruti | 2022-02-03 | 2022-02-12 | 2022-02-04 |  | 100%
| Design login page layout. | Layout Design | In Progress | Salil & Shreyas | 2022-02-03 | 2022-02-12 | 2022-02-04 |  | 40% | In Progress | Low
|  | Database design and connectivity | In Progress | Salil & Shreyas | 2021-10-20 | 2022-02-12 | 2022-02-04 |  | 40%
| Design region selection layout on google map with database mapping to retrieve N,P,K value as per predefined region. | Layout Design, Database query | In Progress | Shriya Dilliwale, Nikhil | 2022-02-03 | 2022-02-12 | 2022-02-04 |  | 70% | Complete | High
|  | Database desing and connectivity | In Progress | shriya dilliwale, Nikhil | 2021-10-20 | 2022-02-12 |  |  | 60%
| Integration of all Layouts |  | On Hold | All | 2021-10-20 | 2022-02-18 |  |  | 40%
Sprint 1 | Design Crop selection layout which mapps with database having crop data and provide selction of crop efficacy to acheive. | Layout Design , Database configuration | In Progress | Rushil | 2021-10-20 | 2021-12-07 |  |  | 10% | On Hold
| Design layout to calculate N,P,K requirement for the crop to acheive effiicacy selected in Task4. | Database configuration | In Progress | [5 empty] | 10% | Overdue
| Design layout to recommend fertilizer from database which fulfils N,P,K requirement caluclated in Task5. | Layout Design | In Progress | [5 empty] | 10%
12
10
10
10
10
15
15
20
20
20
20
10
20
20
15
15
10
20
20
15
15
20
342
65
407

## Version 2
Project Development and Completion Tracker
Porject ID: Version 2
Project Start Date: 15-03-2021 Project End Date:
Porject Descreption: Android and ios application for farmers to monitor growth of crop, fertilizer recomendation and providing regionwise market analysis of crop. (V1) Along with crop growth calendar and stagewise NPK requirement calculation.
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members |  |  | Project Development Student Team Memebers |  |  | Team Lead | Project Domain Expert Team Members (Geolife)
Frond End
Team Lead
Front/Back End
Team Lead
Back End
Front End
Epic: | As a farmer, I should know fertilizer requirement for my crop in my region to fulfill N,P,K.
Story 1: | As a farmer, I should get growth calendar of crop.
Story 2: | As a farmer, I should know growth wise activity reminder of crop.
Story 3: | As a farmer, need stagewise reccomendation of fertilizer to fulfil N,P,K requiremnt of my crop.
Task1: | Design a layout to select crop.
Task2: | Design a layout to select sowing date for crop.
Task3: | Design a layout which will display crop calendar contaiinng stages like watering, pestisides, fertilizer, etc.
Task4: | Create reminders in calendar along with details of each stage with its all possible recommendation.
Task5: | Incorporate NPK requirement to growth calendar stagewise by considering soil contribution and efficacy of crop.
Acceptance Criteria:
1 | Farmer can select crop for sowing in the season out of list with images.
2 | Farmer can select date of sowing with validation.
3 | Completion of stages of crop in calendar are visibille and reminders get pop-up.
4 | When task get completed by farmer, he can input completion of task.
5 | Farmer can view NPK stages requirement and add completion status.
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 1 | Design a layout to select crop. | Creating layout of showing crop categories | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Not Started | Medium
|  | After selecting category, show crop images and selection. | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100%
| Design a layout to select sowing date for crop. | Use calendar API in app. | Complete | Siddhant Oswal, Simon Singh |  | 25-10-2021 |  |  | 100% | In Progress | Low
|  | Show sowing date selction in app. | Complete | Simon Singh, Siddhant Oswal |  | 25-10-2021 |  |  | 100%
| Design a layout which will display crop calendar containg stages like watering, pestisides, fertilizer, etc. | Create database of all crops containg growth stages, watering, pestiside and fertilizer dates. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 50% | Complete | High
|  | Create reminders and display details and recomendation of each stage. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
| When task get completed by farmer, he can input completion of task. | Activity will be in active state till completion. User will make it completed by input. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
|  | User inputs get reflected in database as well. | On Hold | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0% | On Hold
| Farmer can view NPK stages requirement and add completion status. | NPK requirement calculation as per growth stage. | Complete | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Overdue
|  | Include these data in calendar. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 20%

## Student Team
STUDENT INTERN LIST
Sr. No. | Name of Inern | Email Address | Contact | class | Domain (Web, App, Backend)
1 | Prajwal Sah | prajwalsah212@gmail.com | 7776012981 | FY IT DA | ML
2 | Shriya Dilliwale | anitashriya12@gmail.com | 7559361354 | FY IT DA | Flutter, ML | Version 1
3 | Nikhil Chavan | nikhilchavan407@gmail.com | 8369686747 | FY IT - CORE | Flutter | Version 1
4 | Vipul Kumar Singh | vipulkumarbhore@gmail.com | 7764059016 | FY IT - CORE | Flutter | Version 2
5
6
8
9
10
3 | Anjali Bhatt | anjalibhatt601@gmail.com | 830811254 | FY CSE Core 2 | Flutter, ML | Version 1
4 | Shruti Singasane | singasane.shruti2001@gmail.com | 8652233102 | FY CSE Core 2 | Flutter, ML | Version 1
5 | Rushil Jain | rushiljain2001@gmail.com | 9371775841 | FY CSE IS 1 | Flutter, ML | Version 1
7 | Sumeet Sapkal | sumeetspkl@gmail.com | 9112156784 | FY CSE | Flutter, MySQL | Version 2
8 | Sunny Yadav | sunnyyadavtheone@gmail.com | 7878964402 | FY CSE | Flutter, MySQL | Version 2
9 | Siddhant Oswal | oswalsiddhant2001@gmail.com | 8329979013 | FY CSE | Flutter | Version 2
10 | Simon Singh | simonsinghdomain@gmail.com | 7470659108 | FY CSE | Flutter | Version 2
11 | Varun Kapse | varunkapse07@gmail.com | 8830624385 | FY IT - PASSED | ML | Version 2
13 | Rutvi Nair | rutvinar305098@gmail.com | 8141393918 | TY CSE IS 1 | Flutter | Version 2